The ACCJC’s 2004 Action Letter included four focused recommendations:

#2	Implement long-range planning in Information Technology and Learning Resources and
link to budget allocation (previous team recommendation from 1998).

- Not done

#5	Complete a staff diversity plan for greater equity and diversity among all employee group
especially academic administration and full-time faculty (1998 recommendation).

- Evidence?

#6	Develop a comprehensive Educational Master Plan to identify program needs, strengths/
weaknesses and new proposed programs. Revise the program review process, facilities master plan and budget process to show clear linkage between planning processes and resource allocation (1998 recommendation).

- Progress, but not done to the extent that the plan shows direction for
      instructional programs.

#7	Perform an actuarial study to quantify the outstanding liability of post retirement benefits.

- Done per LarrySerot

The prime areas of ongoing concern remain to be planning and linkage.

GCC’s 2007 Midterm Report stated that we:

Met the following recommendations:

#1	Completion of an EMP

- 2005 EMP completed, ongoing updates through program review.

- The college needs an over-arching education plan outlining the direction
                        and priorities for instructional programs (where will our $$’s go…)

#5	Staff Diversity  (ongoing)

- This HR issue is ongoing. Evidence from Ed/HR/IT needed

#6	Linkage in respect to the EMP, planning priorities, and resource allocation

- The college has used planning priorities and program review information 
                       (as available) in a general way regarding budget augmentations and
                       also through the IHAC process.

- There is no solid evidence of linkage in the way the college spends the
                        annual budget (i.e. rollover, capital improvement etc.).

#7	Actuarial study

- Done per Larry Serot

#8	Reserves restored, expenditures not to exceed revenues

- Done per Larry Serot

#9	Evaluation of governance processes (ongoing)

- Governance Review Committee reviews committee issues

#10	CEO Hiring process and transition plan (2005-6)

- Completed

Made significant progress with:

#1	Facilities master plan and Technology Plan (tbd April 2007)

- Check progress of new FMP with Bill Taylor

#2	Linkage of the Technology Plan and Learning Resources Plan to budget.

- Tech plan needs updating by new IT VP.

- Where is the LR plan?

- No linkage to budget.

#3	Restore lost positions and restore staff development.

- Majority of lost positions restored or reorganized

- Staff development funding continues to be problematic

#4	Evaluation timelines and evaluation of management (cabinet to monitor)

- Majority completed….outstanding ?

#5	Staff Diversity Plan (tbd April 2007)

- Is the plan adequate?   We need statistics as evidence

#9	Evaluate CEO and Board

- Processes have been revised. The BOT self-evaluates and evals the CEO.

Note:  The ACCJC states that LINKAGE must include student need, student achievement data, SLOs, 
            and the EMP, FMP and SMP in decision making processes for ALL resource allocation.

PLANS

EMP	Educational Master Plan:  Completed in 2006, includes information and plans at the
departmental/program level.

FMP	Facilities Master Plan:  Historically a plan to build out the campus. Does not address plans
for maintenance of facilities, secondary effects and reallocation of space.

HR 	HR EEO PLAN:       A 13 page plan, no timeline. July 2007.

HR 	Human Resources Strategic Plan (2006-2009):   No timeline

ITP	Informational Technology Plan (2007-2012). Original 1998 document, updated in 2003.

Contains goals and strategies, a computer cascading plan, no timeline.

SMP	Strategic Master Plan:  Campus-wide goals and priorities identified by the planning teams

and incorporated into Program Review.

Staff  		Two Year Faculty & Staff Development Plan & Self Study  (2006-2008)

Development	Includes 3 goals with objectives, no specifics or timeline.

Garfield Plan   Not completed, construction Design to Build plans in the works.

BOT Goals	Annual and aligned with the SMP goals from the planning teams.

Aug. 2008